## Slide 1
1
Probabilistic Extra-Tropical Storm Surge (P-ETSS) 1.0 and ETSS 2.2
Project Status as of 12/02/2016
Issues/Risks
Finances
Scheduling
Project Information and Highlights
Lead: Arthur Taylor, Huiqing Liu, MDL and Steven Earle, NCO
Scope - ETSS 2.2
Extend the CONUS West Coast basin to cover the Gulf of AK with overland information
Create a new Tide version to resolve tide phase shift in CD2, ETP3 and AP3
Experimentally generate max surge + tide above NAVD-88 for 0 to 102 hours
Extend the forecast from 96 to 102 hours
Migrate to the Cray
Discontinue the 5.0 km CONUS and 6.0 km AK grids - AWIPS version 16.1.1 (Dec. 15, 2015) no longer needs them.
General enhancements and bug fixes
Scope - P-ETSS 1.0
P-ETSS – Run ETSS 2.2 using GFS ensemble members to create probabilities
Expected Benefits
Capture surge along the Canadian coast thereby improving the accuracy of the storm surge on the west coast
Extend the lead time for ETSS
Provide probabilistic inundation guidance based on surge and tide for extra-tropical storms
Associated Costs: Federal FTE labor and Contract Support
Funding Sources: MDL Base and Sandy Supplemental
Computational Resources
Current: ETSS 2.1: Use 14 CPUs (1 node) for 37 min on Phase 2
New: ETSS 2.2: Use 14 CPUs (1 node) for 30 min on Cray
New: P-ETSS 1.0: 294 CPU (13 nodes) for 35 min on Cray
- Approved Dec 14, 2015
v1.0 09/14/07
Issues
Mitigation
Milestone (NCEP) | Date | Status
Initial coordination with SPA team | 1/5/2017 | 
Final Code Delivered to NCO | 2/22/2017 | 
Begin prep work for 30 day test | 2/23/2017 | 
IT testing ends | 4/1/2017 | 
Technical Information Notice Issued | 4/6/2017 | 
Users’ - 30-day evaluation begins | 4/21/2017 | 
Users’ - 30-day evaluation ends | 5/20/2017 | 
Management Brief | 6/2/2017 | 
Operational Implementation | 6/6/2017 | 
Potential Management Attention Needed
On Track
Management Attention Required | Potential Management Attention Needed | On Target
G
Y
R
G
G
G
G
MDL
NCO
Responsible Entity
User
Management